## Summary
Project Planner Guide
Sheet Project Information: | Hiển thị thông tin Project
Sheet Project Function: | Hiển thị lịch phân công tổng quan theo các chức năng
Note Details: | Giải thích những chức năng, thảo luận…
Trong mỗi Sheet: | Activities = | Tên công việc / chức năng sẽ thực hiện (copy từ checklist có kèm mã thứ tự) | Lưu ý: | - Không làm thay đổi format của mỗi sheet
| Member = | Tên của thành viên được phân công |  | - Nếu cần thì chèn dòng / cột vào giữa các dòng / cột có sẵn
| Plan start = | Số thứ tự Ngày dự kiến bắt đầu (tính theo ngày bắt đầu dự án) |  | - Phần ngày tháng trên plan (hiển thị theo d/m. Nhưng nhập theo m/d)
| Plan duration = | Số lượng ngày dự kiến hoàn thành công việc
| Actual start = | Số thứ tự Ngày thực sự bắt đầu (tính theo ngày bắt đầu dự án)
| Actual duration = | Số lượng ngày thực sự hoàn thành công việc
| Percent complete = | Phần trăm đánh giá của Cá nhân cho công việc. Mặc định công việc chưa hoàn thành thì ghi 0%

## ProjInfo
Project Information
| Team Name: | gulugulu
| Member List: | Name | GitHub username | Student ID
|  | Khau Dang Nhat Minh | kdnminh-wolfris | 19125011
|  | Nguyen Quoc Khanh Tuyen | peternguyen39 | 19125073
|  | Nguyen Khanh Nguyen | nknguyen19 | 19125109
|  | Nguyen Thieu Khang | nguyenthieukhang | 19125051
| Project ID: | CS162FinalProject |  | 2020-04-19
| Project Name: | Student management system
Requirements
Menu
Data must be stored in file. You can define your own format but it must store all the information as described above.
Be sure that, if I delete a csv file after importing, there is no harm to your system.
Hash password (optional). Tip: SHA1, SHA256…
Dùng mảng động, không dùng vector
Có thể dùng string thay vì char*

## ProjFunctions
Project Planner
[8 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  |  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | time axis 2020-04-19 to 2020-06-14
Code | Activity | Member | START | DURATION | START | DURATION | COMPLETE | 2020-04-19: PERIODS
|  |  | (day) | (count) | (day) | (count) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
1 | All roles
1.1 | Login (3 role: Academic Staff, Lecturer, Student) | Minh | 1 | 14 | 2 | 5 | 50%
1.2 | Show menu | Minh | 1 | 14 | 2 | 5 | 50%
1.3 | View profile info | Minh | 1 | 14 | 6 | 1 | 50%
1.4 | Change password | Minh | 1 | 14 | 3 | 1 | 100%
1.5 | Logout | Minh | 1 | 14 | 2 | 1 | 100%
2 | Academic staff-Class
2.1 | Import students of a class from a csv file. | Tuyen | 1 | 14 | 2 | 2 | 50%
2.2 | Manually add a new student to a class. | Tuyen | 1 | 14
2.3 | Edit an existing student. | Nguyen | 1 | 14 | 2 | 6 | 90%
2.4 | Remove a student. | Nguyen | 1 | 14 | 3 | 1 | 100%
2.5 | Change students from class A to class B | Khang | 1 | 14
2.6 | View list of classes. | Khang | 1 | 14
2.7 | View list of students in a class. | Khang | 1 | 14
3 | Academic staff-Course
3.1 | Create / update / delete / view academic years (2018-2019), and semesters (Fall).
3.2 | From a semester, import courses from a csv file.
3.3 | Manually add a new course.
3.4 | Edit an existing course.
3.5 | Remove a course.
3.6 | Remove a specific student from a course.
3.7 | Add a specific student to a course.
3.8 | View list of courses in the current semester.
3.9 | View list of students of a course.
3.10 | View attendance list of a course.
3.11 | Create / update / delete / view all lecturers.
4 | Academic staff-Score board
4.1 | Search and view the scoreboard of a course.
4.2 | Export a scoreboard to a csv file.
5 | Academic staff-Attendance list
5.1 | Search and view attendance list of a course.
5.2 | Export a attendance list to a csv file.
6 | Lecturer
6.1 | View list of courses in the current semester.
6.2 | View list of students of a course.
6.3 | View attendance list of a course.
6.4 | Edit an attendance.
6.5 | Import scoreboard of a course (midterm, final, lab, bonus) from a csv file.
6.6 | Edit grade of a student
6.7 | View a scoreboard
7 | Student
7.1 | Check-in (1 tuần học/checkin 1 buổi) trong 11 tuần
7.2 | View check-in result.
7.3 | View schedules.
7.4 | View his/her scores of a course.
8 | Additional Functions
8.1 | Hash password
8.2 | Settings
Plan Start là số thứ tự của ngày bắt đầu. Ví dụ bắt đàu từ ngày thứ 2 tức là ngày 7 Apr 202
Plan duration là làm trong bao nhiêu ngày…
…

## NoteDetails
Code | Description | Ghi chú
1.1 | Staff login done (1/3)